**Annex 7: Average Timeframe for Procurement Process**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Time Frame for Procurement Actions** | | | | | | | |
| **With Pre-Qualification25** | | | | | | | |
| **All Values Are Given in Rupees Million & Periods are in Weeks** | | | | | | | |
|  | **More**  **than** | **Between** | | | | | |
|  | **3,000** | **2,000 &**  **3,000** | **1,000 &**  **2,000** | **500 &**  **1,000** | **250 &**  **500** | **100 &**  **250** | **25 &**  **100** |
| Scrutinize PQ application form and approval by TEC26 | 3 | 3 | 3 | 2 | 2 | 2 | 1 |
| Invitation for PQ | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Issue PQ Applications | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| Evaluate PQ applications by TEC27 | 6 | 5 | 5 | 3 | 4 | 3 | 4 |
| Scrutinize bidding document and approval by TEC28 |
| Issue of bidding documents | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Closing of bids | 12 | 10 | 8 | 6 | 6 | 6 | 3 |
| Evaluation by TEC | 12 | 10 | 9 | 8 | 6 | 4 | 3 |
| Review of TEC recommendation by PC | 2 | 2 | 2 | 2 | 2 | 1 | 1 |
| Appeal Procedure/Determination by PC29 | 4 | 4 | 4 | 4 | 4 | 4 |  |
| Approval of the Council | 4 | 4 | 4 | 4 | 4 | 4 |  |
| Issue of Letter of Acceptance | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Contract agreement Signature | 4 | 4 | 4 | 4 | 2 | 2 | 2 |

1. Preparation of PQ application and preparation of design/bidding documents not included
2. Add two weeks days for concurrence from foreign funding agency (if required)
3. Add two weeks for concurrence from foreign funding agency (if required)
4. Add two weeks for concurrence from foreign funding agency (if required)
5. If required

**Time Frame for Procurement Actions**

**Without Pre-Qualification31**

**All values are given in rupees million & periods are in weeks**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **More** |  |  |  | **Between** | |  |  |  |  |  |
|  | **than** |  |  |  |  |  |  |  |  |  |  |
|  | **3,000** | **2,000 &** | **1,000 &** | **500 &** | **250 &** | **100 &** | | **25 &** | **5 &** | **1 &** |  |
|  |  | **3,000** | **2,000** | **1,000** | **500** |  | **250** | **100** | **25** | **5** |  |
| Scrutinize |  |  |  |  |  |  |  |  |  |  |  |
| bidding |  |  |  |  |  |  |  |  |  |  |  |
| documents and | 3 | 3 | 3 | 2 | 2 |  | 2 | 1 | 1 | 1 |  |
| approval by |  |  |  |  |  |  |  |  |  |  |  |
| TEC32 |  |  |  |  |  |  |  |  |  |  |  |
| Invitation for Bid | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  |
|  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| Closing of bids | 12 | 10 | 8 | 6 | 6 |  | 6 | 4 | 3 | 3 |  |
|  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation by | 12 | 10 | 9 | 8 | 6 |  | 4 | 4 | 2 | 2 |  |
| TEC |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| Review of TEC |  |  |  |  |  |  |  |  |  |  |  |
| recommendation | 2 | 2 | 2 | 2 | 2 |  | 1 | 1 | 1 | 1 |  |
| by PC |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| Determination by |  |  |  |  |  |  |  |  |  |  |  |
| Procurement | 2 | 2 | 2 | 2 | 2 |  | 2 | 1 | 1 | 1 |  |
| Committee33 |  |  |  |  |  |  |  |  |  |  |  |
| Appeal | 4 | 4 | 4 | 4 | 2 |  | 2 |  |  |  |  |
| Procedure34 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
| Approval of the | 4 | 4 | 4 | 4 |  |  |  |  |  |  |  |
| Council 35 |  |  |  |  |  |  |  |
| Issue of Letter of | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  |
| Acceptance |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| Contract |  |  |  |  |  |  |  |  |  |  |  |
| agreement | 4 | 4 | 4 | 4 | 2 |  | 2 | 2 | 2 | 1 |  |
| Signature |  |  |  |  |  |  |  |  |  |  |  |

1. Preparation of PQ application and preparation of design/bidding documents not included
2. Add two weeks days for concurrence from foreign funding agency (if required)
3. Add two weeks for concurrence from foreign funding agency (if required)
4. If required
5. If require

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Time Frame for Procurement Actions for Consultancy Services** | | | | | | |
| **All values are given in rupees million & periods are in Days** | | | | | | |
| **When Competitive Procedure (QCBS, QBS, FBS & LCS) or (CQS)** | | | | | | |
|  | **Less**  **than**  **01** | **01-05** | **05-10** | **10-20** | **20-50** | **50-80** |
| Preparation of TOR | 03 | 05 | 07 | 10 | 15 | 21 |
| Preparation of TCE | 03 | 04 | 04 | 04 | 05 | 05 |
| NOL from FFA | 07 | 07 | 07 | 07 | 07 | 07 |
| Inviting EOI | 03 | 03 | 03 | 03 | 03 | 03 |
| Preparation of Long List | 02 | 02 | 02 | 02 | 02 | 02 |
| Preparation of Short List | 05 | 05 | 05 | 05 | 07 | 07 |
| Preparation of RFP | 02 | 02 | 02 | 03 | 03 | 03 |
| NOL from FFA | 07 | 07 | 07 | 07 | 07 | 07 |
| Approve RFP and short list by respective CPC | 07 | 07 | 07 | 10 | 10 | 10 |
| Inviting Proposals | 14 | 14 | 14 | 21 | 21 | 40 |
| Technical Evaluation | 14 | 14 | 14 | 14 | 14 | 14 |
| NOL from FFA | 07 | 07 | 07 | 07 | 07 | 07 |
| Approve Technical Evaluation by respective CPC | 07 | 07 | 07 | 07 | 07 | 07 |
| Opening of Financial Proposal | 10 | 10 | 14 | 14 | 14 | 14 |
| Financial Evaluation | 07 | 07 | 14 | 14 | 14 | 14 |
| Combined / Final Evaluation | 07 | 07 | 07 | 07 | 07 | 07 |
| NOL from FFA | 07 | 07 | 07 | 07 | 07 | 07 |
| Approve Final Evaluation by respective CPC | 07 | 07 | 07 | 07 | 07 | 07 |
| Issue of letter of acceptance | 07 | 07 | 07 | 07 | 07 | 07 |
| Signing of Contract agreement | 07 | 07 | 07 | 07 | 07 | 07 |