## Slide 1: Monitoring & Evaluation
FPA-SKPA Programme
GMME- M&E 1
Lasantha Wickremesooriya
Consultant Strategist

## Slide 2: M&E Defined
Monitoring
Continuous
Ensures project on track
Identifies problems
Evaluation
Assesses whether project is achieving objectives
Periodic
Focuses on outcomes and impacts
Notes: SLIDE CONTENT: According to the World Bank, monitoring is a continuous internal management activity to ensure that project implementation is on track. It involves measuring inputs, activities and outputs, assessing whether they are contributing to achieving the project’s objectives and identifying any existing or potential problems. It helps ensure that the project achieves its defined objectives within a prescribed time frame and budget.
According to the World Bank, evaluation is the process of assessing whether a project is achieving its intended objectives. This may be done periodically by internal managers or by external actors. Evaluation focuses on outcomes and impacts and assesses whether they are contributing to achieving program goals and objectives.
TRAINER NOTE: Let participants know that monitoring and evaluation can also be applied to policy implementation but that the focus of this session will be on monitoring and evaluating projects and programs. More on the basics of M&E can be found in the introduction to M&E presentation in this module.
Ask participants what exposure they have had to monitoring and evaluation in the past. What kinds of tools have they used to monitor and evaluate programs that they have worked on?
For more information on M&E from the World Bank, see the following online training program: http://info.worldbank.org/etools/docs/library/192862/Module4/Module4a.html

## Slide 3: Why do you need M & E?
Define
Define the desired impact of the research team’s stakeholder engagement activities on different projects
Justify
Justify the need and budget for these stakeholder engagement activities.
Increase
Increase the rigor of stakeholder engagement programs, including the potential need to change your strategy and action planning.
Establish
Establish your accountability with the stakeholders

## Slide 5: Complementary Roles of Monitoring and Evaluation
Monitoring
Clarifies program objectives
Links activities and their resources to objectives
Translates objectives into performance indicators and sets targets and baseline
Routinely collects data on these indicators, compares actual results with targets
Reports progress to managers and alerts them to problems
Evaluation
 Analyzes why intended results were or were not achieved
 Assesses specific causal contributions of activities to results
 Examines implementation process
 Explores unintended results
 Provides lessons, highlights significant accomplishment or program potential, and offers recommendations for improvement

## Slide 6: Developing an M & E framework
Determine
Determine who will receive evaluation data
Sponsors? Funders? Community? Stakeholders? Members?
How do you ensure the information will be useful for internal program monitoring purposes?
Map
Map your stakeholder engagement work plan
Prioritize
Prioritize what to evaluate
Select
Select indicators
Decide on
Decide on an approach to measurement
Identify
Identify data collection methods

## Slide 7: Mapping your Project: Illustration

## Slide 8: Ten Steps to Building a Results-Based M&E System

## Slide 9
planning for improvement :
selecting realistic targets
5
1
Conducting a Readiness Assessment
3
selecting key indicators to monitor outcomes
7
using
evaluation information
9
using findings
2
agreeing
on outcomes to monitor and evaluate
4
gathering
baseline data on indicators
6
monitoring
for results
8
reporting findings
sustaining the M&E system
within the organization
10

## Slide 10: Step 1: Conducting a Readiness Assessment
planning for improvement :
selecting realistic targets
5
1
Conducting a Readiness Assessment
3
selecting key indicators to monitor outcomes
7
using
evaluation information
9
using findings
2
agreeing
on outcomes to monitor and evaluate
4
gathering
baseline data on indicators
6
monitoring
for results
8
reporting findings
sustaining the M&E system
within the organization
10

## Slide 11: What Is a Readiness Assessment?
A systematic approach to determine the capacity and willingness of an organization to construct a results-based M&E system
  The approach focuses on: presence or absence of champions, incentives, roles and responsibilities, organizational capacity, and barriers to getting started

## Slide 12: Step 2: Agreeing on Outcomes to Monitor and Evaluate
planning for improvement :
selecting realistic targets
5
1
conducting a readiness assessment
3
selecting key indicators to monitor
outcomes
7
using
evaluation information
9
using findings
2
Agreeing
on Outcomes to Monitor and Evaluate
4
gathering
baseline data
on indicators
6
monitoring
for results
8
reporting findings
sustaining the
M&E system
within the organization
10

## Slide 13: Developing Outcomes
2. Improved awareness of safety measures
1. Improved coverage of HIV programs
Targets:
Baseline:
Indicators:
Outcomes:

## Slide 14: Step 3: Selecting Key Indicators to Monitor Outcomes
planning for improvement :
selecting realistic targets
5
1
conducting
a readiness assessment
3
Selecting Key Indicators to Monitor Outcomes
7
using
evaluation information
9
using findings
2
agreeing on
outcomes to
monitor and evaluate
4
gathering
baseline data
on indicators
6
monitoring
for results
8
reporting findings
sustaining the M&E system
within the organization
10

## Slide 15: Developing Outcomes
2. Improved awareness of safety measures
1. Improved coverage of HIV programs
Targets:
Baseline:
Indicators:
Outcomes:
Number of field level camps per month
Increase in usage of protective care by population

## Slide 16: Indicator Development
“CREAM”
  Clear
  Relevant
  Economic
  Adequate
  Monitorable

## Slide 17: Matrix for Building/Using Indicators
Indicator | Data source | Data collection method | Who will collect data | Frequency of data collection | Cost to collect data | Difficulty to collect | Who will analyze and report data | Who will use data
1. |  |  |  |  |  |  |  | 
2. |  |  |  |  |  |  |  | 
3. |  |  |  |  |  |  |  | 
4. |  |  |  |  |  |  |  | 

## Slide 18: Developing Indicators
Develop your own indicators to meet your needs
Developing good indicators usually takes more than one try
State all indicators neutrally – not “increase in…” or “decrease in…”
Pilot, Pilot, and Pilot!

## Slide 19: Step 4: Gathering Baseline Data on Indicators
planning for improvement :
selecting realistic targets
5
1
conducting a readiness assessment
3
selecting key indicators to monitor
outcomes
7
using
evaluation information
9
using findings
2
agreeing on
outcomes to
monitor and evaluate
4
Gathering Baseline Data
on Indicators
6
monitoring
for results
8
reporting findings
sustaining the
M&E system
within the organization
10

## Slide 20: Baseline Data and Sources
Baseline data:
  Measurements to find out - where are we today?
Primary source:
  gathered specifically for the project
Secondary source:
  collected for another purpose
  can save money but be careful to ensure that it is truly the information you need

## Slide 21
Conversation with Concerned Individuals
Community Interviews
Field Visits
Reviews of Official Records (MIS and admin data)
Participant Observations
Key Informant Interviews
Focus
Group
Interviews
Panel
Surveys
Censuses
Field Experiments
Informal/Less Structured Methods
Formal/More Structured Methods
One-Time Surveys
Direct Observations
Surveys

## Slide 22: Developing Outcomes
2. Improved awareness of safety measures
1. Improved coverage of HIV programs
Targets:
Baseline:
Indicators:
Outcomes:
Number of field level camps per month
Increase in usage of protective care by population
16 field level camps per month
Percentage usage is 62% amongst population

## Slide 23: Step 5: Planning for Improvement: Selecting Realistic Targets
Planning for Improvement :
Selecting Realistic Targets
5
1
conducting a readiness assessment
3
selecting key indicators to monitor
outcomes
7
using
evaluation information
9
using findings
2
agreeing on outcomes to
monitor and evaluate
4
gathering
baseline data
on indicators
6
monitoring for results
8
reporting findings
sustaining the
M&E system
within the organization
10

## Slide 24: Identifying Expected or Desired Level of Improvement Requires Targets
Desired Level of Improvement
Assumes a finite and expected level of inputs, activities, and outputs
Baseline Indicator Level
Target Performance
Desired level of performance to be reached within a specific time
+
=

## Slide 25: Developing Outcomes
2. Improved awareness of safety measures
1. Improved coverage of HIV programs
Targets:
Baseline:
Indicators:
Outcomes:
Number of field level camps per month
Increase in usage of protective care by population
16 field level camps per month
Percentage usage is 62% amongst population
20 field level camps per month
Percentage usage of 77% by 2023 amongst population

## Slide 26: Caution:
It takes time to observe the effects of improvements, therefore:
  Be realistic when setting targets
  Avoid promising too much and thus programming yourself to fail

## Slide 27: Step 6: Monitoring for Results
planning for improvement :
selecting realistic targets
5
1
conducting a readiness assessment
3
selecting key indicators to monitor
outcomes
7
using
evaluation information
9
using findings
2
agreeing on outcomes to
monitor and evaluate
4
gathering
baseline data
on indicators
6
Monitoring for Results
8
reporting findings
sustaining the
M&E system
within the organization
10

## Slide 28: Key Types of Monitoring
Results Monitoring
Implementation Monitoring
Outcomes
Impacts
Results
Inputs
Activities
Outputs
Implementation

## Slide 29: Implementation Monitoring Links to Results Monitoring
Means and Strategies (Multi-year and Annual Work Plans)
Means and Strategies (Multi-year and Annual Work Plans)
Means and Strategies (Multi-year and Annual Work Plans)
Monitor
results
Monitor
Implementation

## Slide 30: Step 7: Using Evaluation Information
planning for improvement :
selecting realistic targets
5
1
conducting a readiness assessment
3
selecting key indicators to monitor
outcomes
7
Using Evaluation Information
9
using findings
2
agreeing on outcomes to monitor and evaluate
4
gathering
baseline data
on indicators
6
monitoring
for results
8
reporting findings
sustaining the
M&E system
within the organization
10

## Slide 31: Evaluation Means Information on:
Strategy | Whether we are doing the right things Rationale/justification Clear theory of change
Operation | Whether we are doing things right Effectiveness in achieving expected outcomes Efficiency in optimizing resources Client satisfaction
Learning | Whether there are better ways of doing it Alternatives Best practices Lessons learned

## Slide 32: Step 8: Reporting Findings
planning for improvement :
selecting realistic targets
5
conducting a readiness assessment
3
selecting key indicators to monitor
outcomes
7
using
evaluation information
9
using findings
2
agreeing on outcomes to
monitor and evaluate
4
gathering
baseline data
on indicators
6
monitoring
for results
8
Reporting Findings
sustaining the
M&E system
within the organization
10
1

## Slide 33: Reporting Findings
Provides information on status of projects, programs, and policies
Yields clues to problems
Creates opportunities to consider changes
Provides important information over time on trends and directions
Helps confirm or challenge theory of change

## Slide 34: Step 9: Using Findings
planning for improvement :
selecting realistic targets
5
1
conducting a readiness assessment
3
selecting key indicators to monitor
outcomes
7
using
evaluation information
9
Using Findings
2
agreeing on
outcomes to
monitor and evaluate
4
gathering
baseline data on
indicators
6
monitoring
for results
8
reporting findings
sustaining the
M&E system
within the organization
10

## Slide 35: Strategies for Sharing Information
Empower the media
Add information on internal and external Internet sites
Publish annual budget reports
Engage stakeholders and citizen groups
Strengthen governance oversight
Strengthen the function of internal audit & risk management
Share and compare results findings with development partners

## Slide 36: Step 10: Sustaining the M&E System within the Organization
planning for improvement :
selecting realistic targets
5
1
conducting
a readiness assessment
3
selecting key indicators to monitor
outcomes
7
using
evaluation information
9
using findings
2
agreeing on outcomes to
monitor and evaluate
4
gathering
baseline data
on indicators
6
monitoring
for results
8
reporting findings
Sustaining the M&E System within the Organization
10

## Slide 37: Critical Components Crucial to Sustaining
Demand
Clear roles and responsibilities
Trustworthy and credible information
Accountability
Capacity
Incentives

## Slide 38: Concluding Comments
The demand for capacity building never ends!
Keep your champions on your side and help them!
Establish the understanding with the relevant stakeholders
Look for every opportunity to link results information to budget and resource allocation decisions
(continued on next slide)

## Slide 39: Concluding Comments (cont.)
Begin with pilot efforts to demonstrate effective results-based monitoring and evaluation
Monitor both implementation progress and results achievements
Complement performance monitoring with evaluations to ensure better understanding of organizational results